## Sheet1
Risk Assessment Summary
Probability of Risk Occurance | High |  |  | -Inaccurate Project Timeline | -Incorrect Specification | -Scheduling Conflicts
| Medium-High | -Overlapping of Artifact creation/Duplication of work |  | -Requirements Change | -Lack of GUI programming experience
| Medium |  |  |  |  | -Lack of direction from customer
Low-Medium
| Low | -Tool availability |  |  | -Project Member(s) Leaving
|  | Low | Low-Medium | Medium | Medium-High | High
Consequence of Risk Impact